## Sheet1
Task | Time Finished
Create Game class | 1
Create State class | 1
Create Board class | 1
Parser: Take input | 2
Parser: Split command on delimiters | 2
Parser: Check command for validity | 3
Parser: Direct command to function | 5
Print out board | 3
Undo function | 7
Create left operator | 4
Create right operator | 4
Create forward operator | 4
Check operator validity | 5
Perform move | 6
Termination condition check | 9
Report game results | 5
Open port on server | 9
Read input | 5
Check for password authentication | 8
Send output | 3
Find possible moves for a piece | 4
Random Algo: Check obvious moves | 8
Random Algo: Pick random move | 8
Set base structure for difficulty | 7
|  | Time Spent | Ideal Backlog | Actual Backlog
|  | 0 | 24 | 24
|  | 1 | 22 | 21
|  | 2 | 19 | 19
|  | 3 | 16 | 16
|  | 4 | 14 | 12
|  | 5 | 11 | 8
|  | 6 | 8 | 7
|  | 7 | 6 | 5
|  | 8 | 3 | 2
|  | 9 | 0 | 0