## Sprint1
Task | Time Finished
Create Game class | 1
Create State class | 1
Create Board class | 1
Parser: Take input | 2
Parser: Split command on delimiters | 2
Parser: Check command for validity | 3
Parser: Direct command to function | 5
Print out board | 3
Undo function | 7
Create left operator | 4
Create right operator | 4
Create forward operator | 4
Check operator validity | 5
Perform move | 6
Termination condition check | 9
Report game results | 5
Open port on server | 9
Read input | 5
Check for password authentication | 8
Send output | 3
Find possible moves for a piece | 4
Random Algo: Check obvious moves | 8
Random Algo: Pick random move | 8
Set base structure for difficulty | 7
|  | Time Spent | Ideal Backlog | Actual Backlog
|  | 0 | 24 | 24
|  | 1 | 22 | 21
|  | 2 | 19 | 19
|  | 3 | 16 | 16
|  | 4 | 14 | 12
|  | 5 | 11 | 8
|  | 6 | 8 | 7
|  | 7 | 6 | 5
|  | 8 | 3 | 2
|  | 9 | 0 | 0

## Sprint2
Task | Time Finished
Create Min-Max Algorithm function | 0
Create Alpha-Beta pruning function | 1
Create Evaluation Function | 0
Min-Max: Evaluation of each piece | 9
Min-Max: Assign Value of board | 5
Min-Max: Returning Max/Min value | 8
Evaluation Function: Create Tree for moves | 4
Evaluation Function: Rank child nodes | 5
Alpha-Beta: Prune Min-Max | 11
Aplha-Beta: make more effiecent | 12
Execute Min-Max Algorithm | 9
Execute Alpha-Beta pruning | 12
Execute Evaluation Function | 8
Fix Display-to-screen errors | 2
Implement Human-AI: Min-Max | 10
Implement Human-AI: Aplha-Beta | 12
Implement Human-AI: Evaluation Function | 9
Implement AI-AI in general | 7
Fix server-client AI-AI issues | 3
Implement AI-AI: Min-Max | 10
Implement AI-AI: Aplha-Beta | 12
Implement AI-AI: Evaluation Function | 8
Implement AI Difficulty: Easy | 0
Implement AI Difficulty: Medium | 10
Implement AI Difficulty: Hard | 12
|  | Time Spent | Ideal Backlog | Actual Backlog
|  | 0 | 25 | 22
|  | 1 | 23 | 21
|  | 2 | 21 | 20
|  | 3 | 19 | 19
|  | 4 | 17 | 18
|  | 5 | 15 | 16
|  | 6 | 13 | 16
|  | 7 | 11 | 15
|  | 8 | 9 | 12
|  | 9 | 7 | 9
|  | 10 | 5 | 6
|  | 11 | 3 | 5
|  | 12 | 0 | 0

## Sprint3
Task | Time Finished
Update Board-Game Layout | 3
Convert click to move | 5
Creation of GUI Class | 0
GUI Client: Added functionality to buttons | 3
GUI Client: Connecting to server | 2
GUI Client: Sending move to server | 3
GUI Client: Interpret server responses | 5
GUI Client: Display board | 1
GUI Client: Fixed row and columns | 2
GUI Client: Layout design | 2
GUI Client: Added icons | 2
GUI Client: Added buttons | 2
GUI Client: Update Color Scheme | 4
GUI Client: Improve efficiency | 5
GUI Client: Fix functionality of buttons | 4
GUI Client: Updated connection issues | 4
GUI Client: Password screen | 4
GUI Client: Centering client | 4
GUI Client: Connection functionality | 2
GUI Client: Allow insensitive password | 5
|  | Time Spent | Ideal Backlog | Actual Backlog
|  | 0 | 20 | 20
|  | 1 | 16 | 18
|  | 2 | 12 | 14
|  | 3 | 8 | 9
|  | 4 | 4 | 5
|  | 5 | 0 | 0