## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Sprint 1
| Sprint 1 Burndown | Sprint 1 - Sprint 1 Burndown
| # Backlog Features vs Time Spent | Sprint 1 - # Backlog Features v
| "All Drawings from the Sheet" | Sprint 1 - Drawings

## Sprint 1 - Sprint 1 Burndown
Sprint 1 Burndown
Task | Time
Create Game class
Create State class
Create Board class
Parser: Take input
Parser: Split command on delimiters
Parser: Check command for validity
Parser: Direct command to function
Print out board
Undo function
Create left operator
Create right operator
Create forward operator
Check operator validity
Perform move
Termination condition check
Report game results
Open port on server
Read input
Check for password authentication
Send output
Find possible moves for a piece
Random Algo: Check obvious moves
Random Algo: Pick random move
Set base structure for difficulty

## Sprint 1 - # Backlog Features v
# Backlog Features vs Time Spent
Time Spent | Ideal Backlog | Actual Backlog
0 | 24 | 24
1 | 21.6 | 24
2 | 19.2 | 20
3 | 16.8 | 20
4 | 14.4 | 20
5 | 12 | 13
6 | 9.6 | 13
7 | 7.2 | 7
8 | 4.8 | 3
9 | 2.4 | 1
10 | 0 | 0